## Slide 1: CY 2021 ICT Unit Revised Work and Financial Plan
Maria veroniCa a. ESLAO
ICT Unit Head (Sr. EDS, PMED)
1st Regular Manteam Meeting
07 January 2021

## Slide 2
NEDA Program of Expenditure Classification (Specific Activities) | 2021 Target | Timeline | Actor | Budgetary Requirements | Remarks
ISO |  |  |  |  | 
IS Development QOP | 1 QOP updated and maintained | July to December 2021 |  |  | 
IS Development Coding Standards | 1 IS Development Coding Standards prepared | July to August 2021 |  |  | 
NRO 1 ISSP | 1 ISSP 2023-2024 updated | July to December 2021 |  |  | 
Information Security and Management System Policy Components: -Usage Policy of NRO 1 Laptops -Usage Policy of NRO 1 Google Workspace -Cyber Security -Others stated in ISO 27001 | 1 ISMS Policy prepared | July to September 2021 |  |  | 
ISO, Plans, Policies and Guidelines

## Slide 3
NEDA Program of Expenditure Classification (Specific Activities) | 2021 Target | Timeline | Actor | Budgetary Requirements | Remarks
Enhancement of the ePPMP | 1 consultation meeting conducted 1 ePPMP enhanced | July 2021 July to August 2021 |  |  | 
Enhancement of the eRPMES | 1 consultation meeting with MED conducted | July 2021 |  |  | 
Contactless eDTR | 1 contactless eDTR deployed, operationalized and maintained | June to December 2021 |  |  | 
eRDIP | 1 consultation meeting conducted 1 eRDIP deployed, operationalized and maintained | August 2021 September to December 2021 |  |  | 
RDC Resolutions Monitoring System | 1 consultation meeting with RDC Unit conducted 1 list of IS Dev updated | July 2021 |  |  | 
Information Systems Development

## Slide 4
Activity | 2021 Target | Time-frame | Responsible Staff | Budgetary Requirements | Remarks
ICT Resources Monitoring & Maintenance |  |  |  |  | 
ICT Resources and Digital Assets Inventory | 1 inventory prepared / maintained / updated | January – February 2021 |  |  | 
Information Resources, Databases and Digital Assets Backup and Archiving | 100% of information resources, databases and digital assets | Daily |  |  | 
ICT Resources Preventive Maintenance and Troubleshooting | 100% of NRO ICT resources | Q1 – Q4 2021 |  |  | 
Network Assessment and Monitoring Report Components: -Data Collection -Report preparation | quarterly | January – December 2021 |  |  | 
ICT Network Infrastructure

## Slide 5
Activity | 2021 Target | Time-frame | Responsible Staff | Budgetary Requirements | Remarks
Information Security |  |  |  |  | 
Digital Security Inspection | 4 quarterly inspections conducted 4 quarterly reports prepared | Same schedule with preventive and maintenance of ICT equipment March, June, September, December (1st wk) |  |  | 
Privacy Impact Assessment (Systems & Infra) | 1 PIA conducted | Q2 & Q4 2021 |  |  | 
Vulnerability Assessment and Penetration Testing (Systems & Infra) | 1 VAPT conducted | Q2 & Q4 2021 |  |  | 
Procurement Services |  |  |  |  | 
TA to Procurement of ICT Resources | 100% of requests provided with TA | As need arises |  |  | 
Establish Cloud Service Management Platform | 1 cloud service management platform acquired | Q4 2021 |  |  | 
ICT Network Infrastructure

## Slide 6
Activity | 2021 Target | Time-frame | Responsible Staff | Budgetary Requirements | Remarks
Service Management |  |  |  |  | 
TA to Online Meetings/Webinars | 100% of TA requests provided | January – December 2021 |  |  | 
NRO 1 Website Management c/o Allan | 1 website maintained / updated | January – December 2021 |  |  | 
Web content uploading | 100% of content uploading requests done | As need arises |  |  | 
ICT Services Trainings and Webinars | 12 trainings / webinars conducted | January – December 2021 |  |  | 
Survey on Commonly-Used Software and Applications | 1 survey conducted | Q1 2021 |  |  | 
Other ICT-related technical support | 100% of ICT-related technical support requests done | January – December 2021 |  |  | 
ICT Services

## Slide 7
THANK YOU